## Estimates
Work package | Track | Best case (d) | Expected | Worst case (d)
Discovery & requirements | Core | 8 | 12 | 20
Solution architecture | Core | 5 | 8 | 15
Data model | Core | 4 | 6 | 11
Backend: core services | Core | 18 | 25 | 45
Backend: integrations | Core | 10 | 16 | 34
Frontend: main flows | UI | 15 | 22 | 38
Frontend: admin | UI | 7 | 11 | 20
Migration scripts | Data | 5 | 9 | 22
QA cycle 1 | Core | 8 | 12 | 20
QA cycle 2 | Core | 5 | 8 | 14
UAT & fixes | Core | 10 | 15 | 30
Release & handover | Core | 3 | 5 | 12